## Plan
Team Workflow Planning Framework
Overview
|  | Qi Feng | Alexander Marzullo | Jayln Campbell
|  | Jeff Woda |  | Alex Gold
|  | Back end | API | Front End | Target | Completed
Start up | Git Hub | connect | connect | connect | Date | Date
| React App Framework Load |  |  |  | 2021-04-01 | 2021-04-01 | 1 | 2021-04-03
Log In | Use Registration | Passport | Api sign up | Sign Up Screen | 2021-04-06 |  | 0
| User Log in | Passport | Api log in | Log in screen | 2021-04-06 |  | 0
| Profile Input | DB | API Post | Profile Input Page | 2021-04-08 |  | 0
Core Setup | Parameters Selection | DB | API POST | Parameter Selection Page | 2021-04-10 |  | 0
| Questioinaire Input | DB | API POST | Questionaire Interface | 2021-04-13 |  | 0
| Algo Process | JS |  |  | 2021-04-15 |  | 0
| Matched Database | DB | API GET | Suggested Match Page | 2021-04-15 |  | 0
MATCH Process |  |  | API GET | User Selection = BIO Statement from Profile | 2021-04-15 |  | 0
| Matched Database | DB | API POST/GET | Like Page | 2021-04-15 |  | 0
| Matched Database | DB | API GET | Match Page | 2021-04-15 |  | 0
|  |  | Heroku Deployment and final Testing |  | 2021-04-17 |  | 0
|  |  | Presentation |  | 2021-04-20 |  | 0

## Overview
[7 empty] | 1.Backend Functionality | Heroku
|  |  | APP | APP |  |  | User Log In | 2 Libraries
|  | Backend | APP | APP | Front End |  | Node Express
[6 empty] | Questionaire | Mongo DB
| List | Main DB | User Log In/Reg |  | Navigation Menu | Profile | Get Post Routes
| 100% | profile Table | Profile |  | Profile Page | Parameters
5 Buckets | 80% | Parameters Table | Parameters | User Input | Parameters Page | Matches | 2. Front End React
0-2.5 |  | Answer Table | Questionaire |  | Questionaire Page | Likes | React
2.5-4.5 |  |  |  | Algo |  |  | Get Post Routes
4.5-6.5 |  | Algo js |  |  | Suggested Match
6.5-8.5 |  |  |  | Suggested Match List | Likes Page/Feature
8.5+ |  |  |  | Match Action | Actual Match
|  | 1 | Text Conversation | 2-3 | Text Page ?
|  | 2 | Phone call | 1-2 | Phone Call Functionality
|  | 3 | Picture Sharing option | unlock Level | Picture Page
|  | 4 | video calling |  |  | Dating
|  |  | Response Score | number of days

## Database
Authentication
| UUID Table | UUID | [7 empty] | Screen Names
|  | login Name | email | [6 empty] | availability
|  | Password | password
| Profile Table | login Name
UUID
|  | Screen Name | string | (check availability)
|  | Sex | male | female
Main DB |  | D.O.B | age
USER UUID |  | Race | black | white | yellow | brown | striped
|  | body style | skinny | fit | athletic | average | a few extra | voluptous | heafty
|  | Algo Score | calculated
|  | bio/self | string
| Parameters Table | UUID
|  | age | 20 | 25 | range
|  | Sex | male | female | boolean
|  | Body style |  |  | various
|  | race |  |  | various
Questionaire Table
|  | UUID | [7 empty] | Filtered Array of Suggested Matches
|  | question 1 | Numeric Value User Assigned |  |  |  | ALGO
|  | question 2 | Numeric Value User Assigned | [6 empty] | Screen display of bio
|  | etc | [7 empty] | user selects:
Actual Matches/likes
| Match Table | UUID
|  | Matches | TRUE | boolean | FALSE | => removes Match
|  | user Choice | FALSE | boolean | TRUE | => Like
|  | Matched | FALSE | boolean | TRUE | => Match

## Profile
| Backend | Middle Man | Front End
Profile Input

## Sheet5
|  | 100 W | 10 W
| Suggested Match | Likes | Matched
Larry | Read Bio | YES | Bingo
|  | 10M | 100M
Suggested Match
Mary | Read Bio | YES | Bingo

## Sheet1
222000
2220
8880
| 11100 | 1565
13
75
1653
690000
2021-04-03
27600 | 2021-07-02
3 | 2021-05-08
200.15
1675
1875.15
222222
6111.105
2138.8868
3972.2183